## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | SWEN-261-05-5
Testing Team Name | fill in when doing cross-team testing (waiting to get team 6 cross test back)

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a helper I want to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page. | Pass |  | Pass
| Given that I am not on the Needs page when I choose the Needs page then I am taken to the Needs page. | Pass |  | Pass
| Given that I am on the Needs page when there are needs in the cupboard then I see each need and short description. | Pass |  | Pass
| Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket. | Pass |  | Pass
As a User I want to be able to login so I can modify the website accordingly | Given A login option when I log in as a customer then I expect to login as a helper, and have permissions to add to cart | Pass |  | Pass
| Given A login option when I log in then I expect to login as an admin with the admin login info. | Pass |  | Pass
| Given A logout option when I log out then I expect to no longer be logged in and be redirected to a login page | Pass |  | Pass
As a Admin I want to log in and be able to modify the catalog of pets that are available at the shelter | Given that I am on the u-fund site when I am not admin the modify page should not be visiable | Pass |  | Pass
| Given an admin login when I select a specific animal then I expect to be able to modify the catalog of available pets, including adding new ones, removing, and modifying existing animals. | Pass |  | Pass
As a User I want to be able to search and see what pets are available to fit my liking | Given any login when I search for a pet using its name then I expect to see the information of the pet corresponding with my search. | Pass |  | Pass
SPRINT 3 DEV
As a Admin I want to view an admin tab | Given any check out by a helper When I click on the admin panel Then I would like to view the transactions |  |  | Pass
| Given in the admin tab when check a user then I can modify the user's permission level |  |  | Pass
As a User I want to view 10% Features on the website | Given any user views the dashboard when I check dashboard Then I view the training videos |  |  | Pass
| Given any user views the dashboard when I click dashboard Then I view the goal/progress bar (not implemented yet) |  |  | Pass